## Monthly report
Monthly progress report
Fill in the white cells. The completion rate is calculated for you.
Month | October 2026
Team or department | Marketing team
Prepared by | Sarah Ahmed
Report date | 2026-10-31
Month summary
Planned tasks | 24
Completed tasks | 19
Overdue tasks | 3
Completion rate
Key achievements
Achievement | Project | Owner | Completed on | Impact
Launched the back-to-school campaign | Q4 campaigns | Sarah Ahmed | 2026-10-08 | 1,200 new store visits
Designed the new ad identity | Q4 campaigns | Reem Hassan | 2026-10-14 | Approved on the first review
Published 12 blog articles | Content | Omar Saleh | 2026-10-29 | Search traffic up 18%
What slipped, and why
Late work | Owner | Reason | New date | Status
Product intro video | Omar Saleh | Script approval was delayed | 2026-11-12 | Postponed
Pricing page update | Reem Hassan | Waiting on the new plans decision | 2026-11-05 | On hold
Challenges and support needed
Challenge | Impact | Support needed
Urgent requests from sales | Two planned tasks slipped | One channel for sales requests, with an owner and a date
Content sign-off goes through three people | An extra week per piece | One approver
Next month's priorities
Rank | Goal | Owner | Date
1 | Launch the Black Friday campaign | Sarah Ahmed | 2026-11-20
2 | Finish the intro video | Omar Saleh | 2026-11-12
3 | Update the pricing page | Reem Hassan | 2026-11-05

## How to use
How to use the monthly progress report template
1. Fill in the report details at the top: month, team, who prepared it, and the date.
2. Enter the month's numbers in the summary: planned, completed, and overdue. The completion rate calculates itself.
3. Write achievements by their impact, not their effort. Give each slipped item its reason and new date, then rank next month's priorities.
4. This file is a report, not a task list, so it does not import into Fareeqy. In Fareeqy these numbers appear in the reports with no sheet to fill: fareeqy.com/features/tracking-reports/en
Block | What to write | Tip
Month summary | How many tasks were planned, completed, and overdue. | Take the numbers from the team's task list, not from memory
Key achievements | What was done, by whom, when, and its impact. | One number for the impact is enough
What slipped, and why | The late work, its reason, and its new date. | State the reason without blame
Challenges and support needed | What slowed the team and what it needs from management. | Ask for a specific decision
Next month's priorities | Three ranked goals, each with an owner and a date. | Most important first
The file contains no macros and no external links.