## Status report
Project status report
Fill in the white cells and pick statuses from the dropdowns. The completion rate calculates itself.
Project | Booking app launch
Project manager | Khaled Omar
Reporting period | 13 to 26 October 2026
Report date | 2026-10-26
Health
Overall | At risk
Schedule | At risk
Scope | On track
Resources | On track
Progress
All tasks | 50
Completed tasks | 31
Completion rate
Summary
Interface design and payment integration are done. Performance testing is a week late because the test environment was not ready, and we need a decision on the SMS provider before 30 October.
Key milestones
Milestone | Planned date | Expected date | Status
Designs approved | 2026-10-10 | 2026-10-10 | Done
Payment gateway connected | 2026-10-24 | 2026-10-24 | Done
Performance testing | 2026-10-31 | 2026-11-07 | Late
Beta launch | 2026-11-15 | 2026-11-15 | On time
Risks and blockers
Risk or blocker | Impact | Owner | Action | Date
Test environment not ready | High | Omar Saleh | Request a temporary server from infrastructure | 2026-10-29
SMS provider not chosen yet | Medium | Khaled Omar | Present two options to management | 2026-10-30
Decisions needed
Decision | Who decides | Needed by
Choose the SMS provider | Sarah Ahmed | 2026-10-30
Plan for the next period
Work | Owner | Date
Finish performance testing | Omar Saleh | 2026-11-07
Prepare the beta tester list | Reem Hassan | 2026-11-10
Write the short user guide | Noura Ali | 2026-11-12

## How to use
How to use the project status report template
1. Fill in the project details and the reporting period at the top.
2. Pick the overall health, schedule, scope, and resources from the dropdowns: On track, At risk, or Off track. Each one colours itself.
3. Write a three-line summary, then the milestones, the risks with an owner and an action for each, and the decisions you need from management.
4. This file is a report, not a task list, so it does not import into Fareeqy. In Fareeqy task status shows up in the project reports with no sheet to fill: fareeqy.com/features/tracking-reports/en
Block | What to write | Tip
Health | Overall health, schedule, scope, and resources. | Pick At risk early, not once it is already late
Progress | The number of tasks, and how many are done. | Take the numbers from the task list, not from memory
Summary | What is done, what slipped, and what you need, in three lines. | Sometimes it is the only part a manager reads
Key milestones | Each milestone, its planned and expected dates, and its status. | The gap between the two dates is the news
Risks and blockers | The risk, its impact, owner, action, and date. | A risk with no owner will not be handled
Decisions needed | The decision, who owns it, and its deadline. | A clear date speeds the decision up
Plan for the next period | The next work, its owner, and its date. | Three items are enough
The file contains no macros and no external links.