## Responsibilities
Phase | Task | Owner | Doers (R) | Consulted (C) | Informed (I) | Due Date | Status | Description
Planning | Define the store's scope and launch goals | Sarah Ahmed | Sarah Ahmed | Khaled Omar; Noura Ali | Leadership | 2026-10-20 | Done | A one-page brief the manager signs off
Planning | Choose the payment provider | Khaled Omar | Khaled Omar | Sarah Ahmed | Reem Hassan | 2026-10-25 | In progress | Compare fees and payout times
Design | Design the product and cart pages | Noura Ali | Noura Ali | Khaled Omar | Sarah Ahmed | 2026-11-03 | In progress
Design | Write product descriptions | Omar Saleh | Omar Saleh | Noura Ali | Sarah Ahmed | 2026-11-05 | Not started | 40 products in the first phase
Build | Build the pages and connect payments | Khaled Omar | Khaled Omar | Noura Ali | Sarah Ahmed | 2026-11-15 | Not started
Launch | Prepare customer service replies | Reem Hassan | Reem Hassan; Omar Saleh | Sarah Ahmed | Whole team | 2026-11-18 | Not started | Expected questions on shipping and returns
Launch | Test an order end to end | Sarah Ahmed | Reem Hassan; Khaled Omar | Noura Ali | Leadership | 2026-11-20 | Not started

## Team
Member | Role | Department
Sarah Ahmed | Project manager | Management
Khaled Omar | Front-end developer | Technology
Noura Ali | UX designer | Design
Omar Saleh | Content lead | Marketing
Reem Hassan | Customer service lead | Operations

## How to use
How to use the task distribution and responsibilities template
1. List your team on the Team sheet. The Owner dropdown is filled from it.
2. On the Responsibilities sheet, write each task under its phase and pick one owner: the person answerable for the result (the A in RACI). A row stays yellow while it has no owner.
3. Add who does the work with them (R), who is consulted before a decision (C), and who only needs to know the outcome (I). Order the tasks inside each phase by importance.
4. Upload the file on Fareeqy's import page, fareeqy.com/import/spreadsheet/en, and each phase becomes a task list, each row a task with its owner and deadline.
Column | What to write | Imported into Fareeqy?
Phase | The stage of work, such as Planning or Build. | Yes, a task list
Task | The work, as a clear verb. The only column the import requires. | Yes, the task title
Owner | One person from the Team sheet, answerable for the result (A). | Yes, matched to a member in the preview
Doers (R) | Who works on the task; can be more than one person. | No, it stays in your file
Consulted (C) | Whose input you need before deciding. | No, it stays in your file
Informed (I) | Who only needs to know the outcome. | No, it stays in your file
Due Date | One deadline, as a date. | Yes, the task's deadline
Status | From the list: Not started, In progress, On hold, or Done. | Done arrives as a completed task
Description | Task details. To keep the R, C, and I names with the task, write them here. | Yes, the task notes
Colours and dropdowns are not imported; only the values in the cells are.
The Team and How to use sheets are skipped by the import.